## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | Completed | None
T002 | Requirements Gathering | Sarah Lee | 2024-04-02 | 2024-04-15 | 14 | In Progress | T001
T003 | Design Phase | Mike Chen | 2024-04-16 | 2024-05-10 | 35 | Not Started | T002
T004 | Development Start | Lisa Wang | 2024-05-11 | 2024-07-15 | 65 | Not Started | T003
T005 | Testing Phase | David Kim | 2024-07-16 | 2024-08-31 | 56 | Not Started | T004
T006 | Final Review & Sign-off | John Doe | 2024-09-01 | 2024-09-01 | 1 | Not Started | T005