## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assigned To | Priority | Status | Dependencies
T001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | John Smith | High | Completed
T002 | Requirements Gathering | 2024-04-02 | 2024-04-15 | 14 | Lisa Chen | High | In Progress | T001
T003 | Design Phase | 2024-04-16 | 2024-05-10 | 35 | Mike Rodriguez | Medium | Not Started | T002
T004 | Development Phase | 2024-05-11 | 2024-07-31 | 92 | Sarah Kim | High | <Not Started | T003
T005 | Testing & QA | 2024-08-01 | 2024-08-31 | 31 | David Lee | High | Not Started | T004
T006 | Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 15 | Emma Watson | Medium | Not Started | T005