## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Responsible Person | Status | Dependencies
T001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Jane Smith | Completed
T002 | 2024-03-16 | 2024-03-25 | 10 | John Doe | In Progress | T001
T003 | Design Finalization | 2024-03-26 | 2024-04-15 | 21 | Lisa Chen | Planned | T002
T004 | Development Phase Start | 2024-04-16 | 2024-06-15 | 61 | Marcus Taylor | Not Started | T003
T005 | Testing & Quality Assurance | 2024-06-16 | 2024-07-15 | 31 | Sophia Kim | <Not Started | T004
T006 | Deployment & Go-Live | 2024-07-16 | 2024-07-18 | 3 | Raj Patel | Not Started | T005