## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Priority | Status
T001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Sarah Johnson | High | Completed
T002 | Requirements Gathering | 2024-03-16 | 2024-03-31 | 16 | Mark Lee | High | In Progress
T003 | Design Phase Finalization | 2024-04-01 | 2024-04-15 | 15 | Lisa Chen | Medium | Planned
T004 | Development Start | 2024-04-16 | 2024-06-30 | 76 | David Kim | High | Not Started
T005 | Quality Assurance Testing | 2024-07-01 | 2024-07-31 | 31 | Emma Ross | High | Scheduled
T006 | Final Review & Sign-off | 2024-08-01 | 2024-08-05 | 5 | Project Manager | Critical | Not Started