## Worksheet
Task ID | Task Name | Start Date | End Date | Responsible Person | Duration (Days) | Status | Dependencies
T001 | Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | John Doe | 1 | Completed | None
T002 | Requirements Gathering | 2024-03-02 | 2024-03-15 | Jane Smith | 14 | In Progress | T001
T003 | Design Phase | 2024-03-16 | 2024-04-10 | Mike Johnson | 35 | Pending | T002
T004 | Development Phase | 2024-04-11 | 2024-06-30 | Sarah Lee | 81 | Not Started | T003
T005 | Testing & QA | 2024-07-01 | 2024-07-31 | David Brown | 31 | Not Started | T004
Project Timeline Report - Version 1.0