## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | Completed
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Business Analysts | In Progress
Design Phase | 2024-03-16 | 2024-03-31 | 16 | UI/UX Team | Not Started
Development Phase | 2024-04-01 | 2024-05-31 | 60 | Development Team | Not Started
Testing & QA | 2024-06-01 | 2024-06-30 | 30 | QA Team | Not Started
Deployment | 2024-07-01 | 2024-07-05 | 5 | IT Operations | Not Started
Post-Launch Review | 2024-07-06 | 2024-07-10 | 5 | Project Manager | Not Started