## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies
Market Research | Alex Morgan | 2024-03-01 | 2024-03-15 | 15 | In Progress | High | None
Product Design | Jordan Lee | 2024-03-16 | 2024-04-05 | 21 | Not Started | High | Market Research Complete
UI/UX Prototyping | Samira Patel | 2024-04-06 | 2024-04-18 | 13 | Planned | Medium | Product Design Finalized
Development Phase | David Chen | 2024-04-19 | 2024-06-30 | 73 | Not Started | Critical | UI/UX Prototyping Approved
QA Testing | Lena Torres | 2024-07-01 | 2024-07-15 | 15 | Not Started | High | Development Phase Complete
Launch Preparation | Rachel Kim | 2024-07-16 | 2024-07-30 | 15 | Not Started | High | QA Testing Passed
Product Launch | Team Lead | 2024-08-01 | 2024-08-03 | 3 | Not Started | Critical | Launch Preparation Complete