## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Party | Status | Priority | Dependencies
T101 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | Completed | High
T102 | Requirements Gathering | 2024-04-02 | 2024-04-15 | 14 | Business Analysts | In Progress | High | T101
T103 | System Design Finalization | 2024-04-16 | 2024-04-25 | 10 | Architect Team | Not Started | Medium | T102
T104 | Development Phase Start | 2024-05-01 | 2024-06-30 | 60 | Development Team | Not Started | High | T103
T105 | Testing & Quality Assurance | 2024-07-01 | 2024-07-31 | 31 | QA Team | Not Started | High | T104
T106 | Deployment & Go-Live | 2024-08-01 | 2024-08-05 | 5 | Operations Team | Not Started | High | T105