## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Priority
T-001 | Project Initiation & Planning | John Doe | 2024-03-15 | 2024-03-25 | 11 | In Progress | None | High
T-002 | <Requirements Gathering | Jane Smith | 2024-03-26 | 2024-04-10 | 15 | Planned | T-001 | High
T-003 | Design Phase (UI/UX) | Mike Johnson | 2024-04-11 | 2024-04-25 | 15 | Pending | T-002 | Medium
T-004 | Development Phase | Sarah Lee | 2024-04-26 | 2024-06-15 | 60 | Not Started | T-003 | High
T-005 | Testing & QA | David Brown | 2024-06-16 | 2024-07-10 | 35 | Planned | T-004 | High
T-006 | Deployment & Go-Live | Lisa Wong | 2024-07-11 | 2024-07-15 | 5 | Not Started | T-005 | Medium