## Worksheet
Task ID | Task Name | Start Date | End Date | Responsible Person | Priority | Status | Duration (Days)
T001 | Project Initiation | 2024-04-01 | 2024-04-05 | John Smith | High | Completed | 5
T002 | Requirements Gathering | 2024-04-06 | 2024-04-18 | Sarah Johnson | High | Completed | 13
T003 | Design Phase | 2024-04-19 | 2024-05-10 | Mike Davis | Medium | In Progress | 22
T004 | Development Phase | 2024-05-11 | 2024-07-15 | Lisa Wong | High | Pending | 65
T005 | Testing & QA | 2024-07-16 | 2024-08-15 | David Brown | High | Pending | 30
T006 | Deployment & Go-Live | 2024-08-16 | 2024-08-25 | Rachel Kim | Medium | Pending | 10