## Worksheet
Task ID | Task Name | Start Date | End Date | Assigned To | Status | Progress (%) | Dependencies | Priority
T-001 | Project Initiation | 2024-04-01 | 2024-04-05 | John Doe | Completed | 100 | None | High
T-002 | Requirements Gathering | 2024-04-06 | 2024-04-15 | Jane Smith | In Progress | 65 | T-001 | High
T-003 | Design Phase | 2024-04-16 | 2024-05-10 | Mike Johnson | Not Started | 0 | T-002 | Medium
T-004 | Development Phase | 2024-05-11 | 2024-07-30 | Sarah Lee | Not Started | 0 | T-003 | High
T-005 | Testing & QA | 2024-08-01 | 2024-08-31 | David Kim | Not Started | 0 | T-004 | High
T-006 | Deployment | 2024-09-01 | 2024-09-15 | Lisa Wong | Not Started | 0 | T-005 | Medium
Total Tasks: |  |  |  |  | 6 | Average Progress: |  | 35%