## Worksheet
Week | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies
Week 1 | Project Kickoff Meeting | Project Manager | 2023-10-02 | 2023-10-06 | Completed | High | -
Week 2 | Requirements Gathering | Business Analyst | 2023-10-09 | 2023-10-13 | In Progress | High | Kickoff Meeting
Week 3 | Design Phase Finalization | UI/UX Designer | 2023-10-16 | 2023-10-20 | Planned | Medium | Requirements Gathering
Week 4 | Development Start | Software Developer | 2023-10-23 | 2023-10-27 | Not Started | High | Design Phase Finalization
Week 5 | Testing & QA Review | QA Engineer | 2023-10-30 | 2023-11-03 | Planned | Medium | Development Start
Week 6 | Client Feedback & Adjustments | Project Manager | 2023-11-06 | 2023-11-10 | Not Started | High | Testing & QA Review