## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Dependencies | Estimated Hours | Actual Hours | Progress (%) | Notes
TSK-001 | Project Kickoff Meeting | Alice Johnson | 2024-03-15 | 2024-03-15 | Completed | Low | None | 2 | 2 | 100% | All stakeholders confirmed attendance.
TSK-002 | Requirements Gathering | Bob Smith | 2024-03-16 | 2024-03-25 | In Progress | Medium | TSK-001 | 10 | 6 | 60% | Initial drafts reviewed by PM.
TSK-003 | UI/UX Design Phase | Carol Davis | 2024-03-26 | 2024-04-10 | Not Started | High | TSK-002 | 15 | 0 | 0% | Design briefs pending approval.
TSK-004 | Development Setup | David Lee | 2024-04-11 | 2024-04-15 | In Progress | Medium | TSK-003 | 8 | 4 | 50% | Environment configured; waiting for design assets.
TSK-005 | Testing & Quality Assurance | Eva Martinez | 2024-04-16 | 2024-05-05 | Not Started | High | TSK-004 | 20 | 0 | 0% | Initial test cases to be developed.