## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Progress (%) | Notes
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | High | Completed | 100% | Initial planning session held successfully.
TSK-002 | Design Phase Review | John Doe | <="text-align:center;">2024-04-15Medium | In Progress | 65% | Design mockups approved by stakeholders.
TSK-003 | Development Setup | Alice Johnson | 2024-04-10 | High | Pending | 0% | Environment configured but not yet tested.
TSK-004 | Client Presentation | Robert Brown | 2024-05-10 | High | Not Started | 0% | Presentation materials under review.
TSK-005 | Final Testing & QA | Sarah Lee | 2024-05-25 | Critical | Not Started | 0% | Must be completed before go-live.