## Worksheet
Task ID | Task Name | Assigned To | Due Date | Status | Priority | Start Date | Progress (%) | Dependencies | Estimated Hours
T001 | Project Kickoff Meeting | Jane Doe | 2024-03-15 | Completed | Low | 2024-03-10 | 100% | None | 2
T002 | Requirement Gathering | John Smith | 2024-04-10 | In Progress | Medium | 2024-03-18 | 65% | T001 | 8
T003 | Design Phase Finalization | Alice Brown | 2024-05-01 | Not Started | High | 2024-04-15 | 0% | T002 | 12
T004 | Development Sprint 1 | Mike Lee | 2024-05-20 | Planned | Medium | 2024-05-05 | 0% | T003 | 20
T005 | User Testing & Feedback | Sarah Wang | 2024-06-15 | Not Started | High | 2024-05-25 | 0% | T004 | 15