## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies | Progress (%)
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | Completed | Low | None | 100
T002 | Requirement Gathering | Jane Smith | 2024-04-02 | 2024-04-10 | In Progress | Medium | T001 | 60
T003 | Design Phase | Mike Johnson | 2024-04-11 | 2024-04-25 | Not Started | High | T002 | 0
T004 | Development Phase | Lisa Brown | 2024-04-26 | 2024-05-31 | Not Started | High | T003 | 0