## Worksheet
Task ID | Task Name | Project Name | Assigned To | Start Date | End Date | Duration (days) | Priority | Status | Dependencies | Progress (%) | Notes
TSK-001 | Project Kickoff Meeting | Phase 1 Development | Jane Smith | 2024-03-15 | 2024-03-16 | 1 | High | Completed | None | 100 | Finalize project scope and objectives.
TSK-002 | Design Wireframes | Phase 1 Development | John Doe | 2024-03-17 | 2024-03-25 | 9 | Medium | In Progress | TSK-001 | 75 | Final wireframes reviewed by product lead.
TSK-003 | Backend API Development | Phase 1 Development | Michael Chen | 2024-03-26 | 2024-04-10 | 15 | High | Not Started | TSK-002 | 0 | Implement user authentication and data storage.
TSK-004 | Frontend UI Implementation | Phase 1 Development | Sarah Kim | 2024-04-11 | 2024-04-25 | 15 | Medium | Planned | TSK-003 | 0 | Align UI with design system.
TSK-005 | QA Testing & Bug Fixing | Phase 1 Development | Linda Walker | 2024-04-26 | 2024-05-05 | 10 | High | Not Started | TSK-003, TSK-004 | 0 | Comprehensive test cycles and defect resolution.