## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | Completed | Low |  | Initial project alignment and objectives set.
T002 | Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-03-25 | In Progress | Medium | T001 | Collect user needs and define functional requirements.
T003 | Design Phase | Mike Johnson | 2024-03-26 | 2024-04-10 | Not Started | High | T002 | Create wireframes and UI mockups.
T004 | Development Start | Alex Chen | 2024-04-11 | 2024-05-30 | Not Started | High | T003 | Begin coding with backend and frontend implementation.
T005 | Testing & QA | Lisa Wong | 2024-06-01 | 2024-06-15 | Not Started | Medium | T004 | Conduct unit, integration, and user acceptance testing.
T006 | Go-Live Deployment | Tom Harris | 2024-06-16 | 2024-06-16 | Not Started | High | T005 | Deploy application to production environment.