## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Progress (%) | Notes
TSK-001 | Project Kickoff Meeting | Alex Rivera | 2024-04-01 | 2024-04-03 | In Progress | High | 60% | Review team roles and responsibilities.
TSK-002 | Design Phase Review | Jordan Lee | 2024-04-05 | 2024-04-10 | Pending | Medium | 0% | Awaiting design documents from UX team.
TSK-003 | Develop Backend API | Sam Chen | 2024-04-11 | 2024-04-25 | In Progress | High | 45% | Finalizing authentication endpoints.
TSK-004 | Frontend UI Implementation | Mia Torres | 2024-04-15 | 2024-05-01 | Not Started | Medium | 0% | Design mockups approved on April 12.
TSK-005 | QA Testing Phase | Raj Patel | 2024-05-05 | 2024-05-15 | Planned | High | 0% | Will begin after backend is complete.