## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Progress (%) | Notes
T001 | Project Initiation & Planning | John Smith | 2024-03-01 | 2024-03-15 | 15 | High | In Progress | - | 60% | Finalize scope and budget.
T002 | Stakeholder Interviews | Anna Lee | 2024-03-16 | 2024-03-25 | 10 | Medium | Planned | T001 | 40% | Schedule sessions with key departments.
T003 | Requirements Gathering | Michael Chen | 2024-03-26 | 2024-04-10 | 15 | High | Not Started | T002 | 0% | Document functional and technical requirements.
T004 | Design Phase | Sarah Kim | 2024-04-11 | 2024-05-15 | 35 | High | Not Started | T003 | 0% | Develop UI/UX wireframes and prototypes.
T005 | Development & Coding | David Park | 2024-05-16 | 2024-07-31 | 75 | Critical | Not Started | T004 | 0% | Build core application modules.