## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | Budget (USD) | Actual Cost (USD) | Progress (%) | Priority
TSK-001 | Project Planning & Scope Finalization | John Smith | 2024-03-15 | 2024-03-25 | 10 | On Track | 15,000 | 12,850 | 95% | High
TSK-002 | <Market Research & Analysis | Sarah Lee | 2024-03-26 | 2024-04-10 | 15 | In Progress | 20,000 | 14,200 | 75% | Medium
TSK-003 | Development Phase – MVP Build | Michael Chen | 2024-04-11 | 2024-05-31 | 60 | Not Started | 75,000 | 0 | 0% | High
TSK-004 | Quality Assurance & Testing | Lisa Wong | 2024-06-01 | 2024-06-30 | 30 | Planned | 18,500 | 16,900 | 85% | Medium