## Worksheet
Task ID | Task Name | Project Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Progress (%)
T-2024-001 | Design Brand Identity | Product Launch 2024 | Sarah Johnson | 2024-03-01 | 2024-03-15 | In Progress | High | 80 | 45 | 75%
T-2024-002 | Develop MVP Backend | Product Launch 2024 | James Lee | 2024-03-05 | 2024-03-25 | Not Started | Critical | 120 | 0 | 0%
T-2024-003 | User Testing Phase | Product Launch 2024 | Lena Park | 2024-03-20 | 2024-04-10 | Planned | Medium | 50 | 0 | 0%
T-2024-004 | Market Strategy Review | Q3 Growth Initiative | Michael Chen | 2024-04-01 | 2024-04-15 | On Track | Medium | 30 | 25 | 83%
T-2024-005 | Final Product Documentation | Product Launch 2024 | Emily Davis | 2024-04-18 | 2024-05-05 | Not Started | Low | 40 | 0 | 0%