## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies | Estimated Hours | Actual Hours
T-001 | Project Planning Workshop | John Doe | 2024-03-15 | 2024-03-17 | In Progress | High | None | 8 | 6
T-002 | Requirement Gathering | Jane Smith | 2024-03-18 | 2024-03-25 | Not Started | High | T-001 | 20 | 0
T-003 | UI/UX Design Phase | Alex Brown | 2024-03-26 | 2024-04-05 | In Progress | Medium | T-002 | 32 | 18
T-004 | Backend Development | Mike Johnson | 2024-04-06 | 2024-05-10 | Not Started | High | T-003 | 60 | 0
T-005 | Testing & QA | Sarah Lee | 2024-05-11 | 2024-05-25 | Not Started | Medium | T-004 | 40 | 0
Total Tasks (5) |  |  |  |  | Total Estimated Hours | Total Actual Hours
Summary |  |  |  |  | 150 | 32