## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies | Notes
T001 | Project Initiation Meeting | John Smith | 2024-04-01 | 2024-04-03 | In Progress | High |  | Review project goals and stakeholders.
T002 | Requirements Gathering | Jane Doe | 2024-04-04 | 2024-04-15 | Not Started | High | T001 | Collect user requirements via surveys and interviews.
T003 | Design Phase | Mike Johnson | 2024-04-16 | 2024-05-10 | Planned | Medium | T002 | Create wireframes and UI mockups.
T004 | Development Start | Sarah Lee | 2024-05-11 | 2024-07-30 | Not Started | High | T003 | Begin coding according to design specs.
T005 | Testing & QA | David Brown | 2024-08-01 | 2024-08-20 | Not Started | High | T004 | Conduct unit, integration, and user acceptance tests.