## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies | Progress (%)
T001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-02 | Completed | Medium |  | 100%
T002 | Requirements Gathering | John Doe | 2024-04-03 | 2024-04-15 | In Progress | High | T001 | 65%
T003 | UI/UX Design Finalization | Sarah Lee | 2024-04-16 | 2024-04-25 | Planned | Medium | T002 | 30%
T004 | Development Phase Start | Mike Chen | 2024-04-26 | 2024-05-15 | Not Started | High | T003 | 0%
T005 | Testing & Quality Assurance | Linda Park | 2024-05-16 | 2024-05-31 | Pending Approval | Critical | T004 | 15%