## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Progress (%) | Notes
T001 | Project Kickoff Meeting | Jane Smith | 2023-10-01 | 2023-10-02 | Completed | High | 100 | Initial planning session held with stakeholders.
T002 | Requirements Gathering | John Doe | 2023-10-03 | 2023-10-15 | In Progress | High | 60 | Interviews with end-users scheduled.
T003 | Design Phase Initiation | Sarah Lee | 2023-10-16 | 2023-10-25 | Planned | Medium | 0 | Wireframes to be reviewed by team lead.
T004 | Development Setup | Mike Chen | 2023-10-26 | 2023-11-05 | Not Started | Low | 0 | Environment configured; waiting for approval.