## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Progress (%)
T-001 | Project Initiation & Planning | John Doe | 2024-03-15 | 2024-03-25 | 10 | In Progress | High | None | 60%
T-002 | Requirement Gathering Workshop | Sarah Lee | 2024-03-26 | 2024-03-31 | 5 | Not Started | Medium | T-001 | 0%
T-003 | Design Phase Finalization | Michael Chen | 2024-04-01 | 2024-04-15 | 15 | Planned | High | T-002 | 20%
T-004 | Development Sprint 1 | Lisa Wong | 2024-04-16 | 2024-05-03 | 28 | Scheduled | High | T-003 | 0%
T-005 | Testing & Quality Assurance | David Kim | 2024-05-04 | 2024-05-31 | 38 | Not Started | Medium | T-004 | 0%
Total Tasks |  |  |  |  | 10 | Status Summary |  | In Progress / Scheduled / Planned / Not Started