## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Estimated Hours | Progress (%) | Notes
T001 | Project Kickoff Meeting | John Smith | 2023-10-03 | 2023-10-05 | In Progress | High | 4 | 75% | Discuss project scope and objectives.
T002 | Requirements Gathering | Jane Doe | 2023-10-04 | 2023-10-15 | Not Started | High | 8 | 0% | Collect user requirements through interviews.
T003 | UI/UX Design Phase | Alex Chen | 2023-10-06 | 2023-10-25 | In Progress | Medium | 12 | 50% | Finalize wireframes and prototypes.
T004 | Development Phase | Sam Wilson | 2023-10-10 | 2023-11-20 | Not Started | High | 40 | 0% | Build core application modules.
T005 | Testing & QA | Taylor Reed | 2023-11-05 | 2023-11-30 | Not Started | Medium | 20 | 0% | Conduct functional and usability testing.
T006 | Deployment | Jordan Lee | 2023-12-01 | 2023-12-05 | Not Started | Low | 4 | 0% | Launch application to production environment.