## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Progress (%) | Dependencies
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-01 | Completed | Low | 100% | N/A
TSK-002 | Requirements Gathering | John Doe | <-being-style="text-align: left;">2024-04-022024-04-15 | In Progress | Medium | 65% | TSK-001
TSK-003 | UI/UX Design Phase | Lisa Chen | 2024-04-16 | 2024-05-10 | Pending | High | 0% | TSK-002
TSK-004 | Development Phase (Frontend) | Mike Rodriguez | 2024-05-11 | 2024-06-15 | Scheduled | Medium | 0% | TSK-003
TSK-005 | Testing & QA Review | Sarah Kim | 2024-06-16 | 2024-07-05 | Pending | High | 0% | TSK-004