## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Duration (days)
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | Completed | Moderate | 1
T002 | Requirements Gathering | Jane Smith | 2024-04-02 | 2024-04-15 | In Progress | High | 14
T003 | UI/UX Design Finalization | Alice Johnson | 2024-04-16 | 2024-05-10 | Pending | Moderate | 35
T004 | Development Phase Start | Bob Lee | 2024-05-11 | 2024-07-31 | Pending | High | 92