## Worksheet
Task ID | Task Name | Owner | Priority | Due Date | Status | Start Date | Duration (Days) | Progress (%) | Notes
TSK-001 | Market Research & Analysis | Alex Chen | High | 2023-09-15 | In Progress | 2023-08-20 | 30 | 65% | Gather competitor data from top three platforms.
TSK-002 | Product Wireframing | Jordan Lee | Medium | 2023-09-20 | Not Started | - | 25 | 0% | Finalize UI layout for mobile and web.
TSK-003 | Beta Testing Launch | Mia Patel | High | 2023-10-05 | Scheduled | 2023-09-30 | 7 | 40% | Recruit 50 users for feedback.
TSK-004 | Onboarding Flow Design | Ryan Kim | Medium | 2023-09-30 | In Progress | 2023-08-25 | 35 | 75% | Improve first-time user retention.
TSK-005 | Post-Launch Analytics Setup | Samira Ahmed | Low | 2023-10-15 | Not Started | - | 15 | 0% | Set up Google Analytics and Mixpanel.