## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Progress (%) | Dependencies
T-001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-03 | Completed | High | 100 | None
T-002 | Requirements Gathering | Sarah Lee | 2024-04-04 | 2024-04-15 | In Progress | High | 65 | T-001
T-003 | UI/UX Design Phase | Mike Chen | 2024-04-16 | 2024-05-10 | Planned | Medium | 0 | T-002
T-004 | Development Sprint 1 | Lisa Wong | 2024-05-11 | 2024-06-05 | Not Started | Medium | 0 | T-003
T-005 | Testing & Quality Assurance | David Kim | 2024-06-06 | 2024-07-15 | Planned | High | 0 | T-004