## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Dependencies | Progress (%) | Notes
T-001 | Project Kickoff Meeting | Jane Smith | 2024-03-15 | 2024-03-15 | Completed | Low |  | 100 | All team members attended and objectives were defined.
T-002 | Requirements Gathering | John Doe | 2024-03-16 | 2024-03-25 | In Progress | Medium | T-001 | 60 | Client feedback sessions scheduled.
T-003 | Design Phase | Sarah Lee | 2024-03-26 | 2024-04-10 | Not Started | High | T-002 | 0 | Wireframes and UI mockups to be finalized.
T-004 | Development Phase | Mike Chen | 2024-04-11 | 2024-05-30 | Not Started | High | T-003 | 0 | Frontend and backend implementation.
T-005 | Testing & QA | Lisa Wong | 2024-06-01 | 2024-06-15 | Not Started | Medium | T-004 | 0 | Unit, integration, and user acceptance testing.