## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Dependencies | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | Completed | Low |  | Initial team alignment and goals setting.
T002 | Requirements Gathering | Sarah Lee | 2024-04-02 | 2024-04-15 | In Progress | Medium | T001 | Collect input from stakeholders.
T003 | Design Phase | Mike Chen | 2024-04-16 | 2024-05-10 | Planned | High | T002 | Develop UI/UX mockups and prototypes.
T004 | Development Phase | Lisa Wong | 2024-05-11 | 2024-07-31 | Not Started | High | T003 | Build application modules and backend.
T005 | Testing & QA | David Kim | 2024-08-01 | 2024-08-31 | Not Started | High | T004 | Perform unit, integration, and user acceptance testing.
T006 | Deployment | Emma Patel | 2024-09-01 | 2024-09-05 | Not Started | Medium | T005 | Deploy to production environment with rollback plan.