## Worksheet
Week | Task Name | Owner | Start Date | End Date | Status | Priority | Progress (%) | Notes
Week 1 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-03 | Completed | High | 100 | Initial alignment with stakeholders.
Week 1 | Requirements Gathering | Jane Smith | 2024-04-04 | 2024-04-10 | <In Progress | High | 65 | Client feedback pending.
Week 2 | UI/UX Design Finalization | Alice Johnson | 2024-04-11 | 2024-04-17 | Planned | Medium | 0 | Design mockups to be reviewed.
Week 2 | Development Sprint 1 | Mike Brown | 2024-04-18 | 2024-04-24 | Blocked | High | 30 | Dependency on third-party API.
Week 3 | Testing Phase (Beta) | Sarah Lee | 2024-04-25 | 2024-05-01 | Scheduled | Medium | 0 | Users to be invited via email.