## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority Level | Status | Estimated Hours | Actual Hours | Start Date | Completion Date | Notes | Responsible Team
TSK-001 | Customer Onboarding Process | John Doe | 2024-04-15 | High | In Progress | 8 | 5.5 | 2024-04-01 |  | Ensure all onboarding documents are signed and delivered to the client portal. | Sales Operations
TSK-002 | Quarterly Sales Forecast Review | Sarah Kim | 2024-05-10 | Medium | Pending | 4 | 0 |  |  | Review past performance, update targets based on market trends. | Sales Planning
TSK-003 | Client Retention Follow-Up | Mike Johnson | 2024-04-28 | High | Completed | 3 | 3 | 2024-04-18 | 2024-04-27 | Client feedback collected and action items documented. | Customer Success
TSK-004 | New Product Pitch Session | Lisa Chen | 2024-05-05 | High | Not Started | 6 | 0 |  |  | Prepare presentation materials and target audience analysis. | Sales Development