## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Estimated Hours | Actual Hours | Progress (%)
TASK-001 | Client Onboarding Setup | Sarah Johnson | 2024-04-01 | 2024-04-15 | In Progress | High | 8 hours | 6 hours | 75%
TASK-002 | Quarterly Sales Report Preparation | Mark Thompson | 2024-04-05 | 2024-04-30 | Not Started | Medium | 16 hours | 0 hours | 0%
TASK-003 | CRM System Update Implementation | Lisa Chen | 2024-04-10 | 2024-05-05 | Scheduled | High | 30 hours | 0 hours | 0%
TASK-004 | Sales Forecast Review Meeting | David Lee | 2024-04-18 | 2024-04-18 | Completed | Low | 4 hours | 4 hours | 100%
TASK-005 | Lead Nurturing Campaign Design | Amanda Wright | 2024-04-20 | 2024-05-10 | In Progress | Medium | 20 hours | 10 hours | 50%