## Worksheet
Task ID | Task Name | Scheduled Date | Priority Level | Status | Responsible Person | Estimated Time (hrs) | Progress (%)
T001 | Project Kickoff Meeting | 2023-10-15 | High | Completed | Sarah Johnson | 2 | 100%
T002 | <Requirements Gathering | 2023-10-20 | High | In Progress | Mark Lee | 8.5 | 60%
T003 | Design Phase Review | 2023-11-05 | Medium | Pending | Lisa Wong | 4 | 0%
T004 | Development Start | 2023-11-10 | High | Not Started | David Chen | 20 | 0%
T005 | QA Testing Phase | 2023-12-01 | High | Planned | Emma Torres | 15 | 0%