## Worksheet
Task ID | Task Name | Scheduled Date | Start Time | End Time | Priority Level | Assigned To | Status | Estimated Duration (hrs) | Resources Required | Dependencies | Notes
T001 | Project Kickoff Meeting | 2024-04-15 | 09:00 AM | 10:30 AM | High | John Doe | Completed | 1.5 | Meeting Room A, projector |  | Review project goals and team roles.
T002 | Market Research Analysis | 2024-04-18 | 14:00 PM | 16:30 PM | Medium | Jane Smith | In Progress | 2 | Access to CRM data, analyst tools | T001 | Compile competitor reports and user trends.
T003 | Prototype Development | 2024-04-25 | 10:00 AM | 13:00 PM | High | Mike Johnson | Pending | 4.5 | Design software, testing tools | T002 | Create UI mockups based on market findings.
T004 | Stakeholder Review Session | 2024-05-02 | 15:30 PM | 17:30 PM | High | Sarah Lee | Not Started | 2.5 | Presentation software, stakeholders list | T003 | Present prototype and gather feedback.