## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | High | Completed | None
T002 | Requirements Gathering | Jane Smith | 2024-04-02 | 2024-04-10 | 9 | High | In Progress | T001 | Finalize user stories and acceptance criteria.
T003 | UI/UX Design Phase | Alex Johnson | 2024-04-11 | 2024-04-25 | 15 | Medium | Planned | T002 | Create wireframes and prototypes.
T004 | Development Phase | Team A | 2024-04-26 | 2024-05-15 | 21 | High | Not Started | T003 | Backend and frontend implementation.
T005 | Testing & QA | Maria Lee | 2024-05-16 | 2024-05-31 | 16 | High | Not Started | T004 | Performance, security, and functional testing.
T006 | Deployment | DevOps Team | 2024-06-01 | 2024-06-01 | 1 | Critical | Not Started | T005 | Launch to production environment.