## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Project Planning Phase | John Doe | 2024-03-01 | 2024-03-15 | 15 | High | In Progress | - | Finalize scope and milestones.
T002 | Resource Allocation | Jane Smith | 2024-03-16 | 2024-03-25 | 10 | Medium | Pending | T001 | Confirm team availability.
T003 | Design Review Meeting | Mike Johnson | 2024-03-26 | 2024-03-28 | 3 | High | Not Started | T002 | Review UI/UX drafts with stakeholders.
T004 | Development Phase | Team A | 2024-03-29 | 2024-05-15 | 68 | High | Not Started | T003 | Build core functionality.
T005 | Testing & QA | Lisa Brown | 2024-05-16 | 2024-06-10 | 45 | Critical | Not Started | T004 | Conduct functional and regression tests.