## Worksheet
Task | Assigned To | Start Date | End Date | Duration (days) | Status | Priority
Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | 1 | Completed | High
Requirements Gathering | Sarah Lee | 2024-04-02 | 2024-04-10 | 9 | In Progress | High
Design Phase Final Review | Mike Chen | 2024-04-11 | 2024-04-15 | 5 | Pending | Medium
Development Start | Alex Rivera | 2024-04-16 | 2024-05-31 | 47 | Not Started | High
Testing & Quality Assurance | Lisa Wong | 2024-06-01 | 2024-06-15 | 15 | Not Started | Medium
Final Deployment & Review | Team Lead | 2024-06-16 | 2024-06-18 | 3 | Not Started | High