## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | 1 | High | Planned | Confirm stakeholders and agenda.
T002 | Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-03-25 | 10 | High | In Progress | Collect input from business units.
T003 | Design Review Session | David Kim | 2024-04-01 | 2024-04-03 | 3 | Medium | Pending | Finalize UI/UX mockups.
T004 | Development Phase Start | Michael Brown | 2024-04-05 | 2024-05-15 | 42 | High | Not Started | Begin backend and frontend coding.
T005 | QA Testing | Lisa Chen | 2024-05-16 | 2024-05-31 | 16 | High | Planned | Conduct full system testing.