## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Notes
T001 | Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | 2024-04-01 | In Progress | High | Review project scope and objectives.
T002 | Design Phase Planning | Mike Chen | 2024-04-03 | 2024-04-15 | Planned | Medium | Finalize wireframes and user flow.
T003 | Frontend Development | Lena Rodriguez | 2024-04-16 | 2024-05-10 | Scheduled | High | Build responsive UI components.
T004 | Client Feedback Session | Team Lead | 2024-05-15 | 2024-05-15 | Pending | High | Gather input on design mockups.
T005 | Final Testing & QA | David Kim | 2024-05-20 | 2024-05-31 | Not Started | High | Conduct full system testing.