## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Duration (Days) | Dependencies
T001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-01 | High | Completed | 1
T002 | Requirements Gathering | Alex Johnson | 2024-04-02 | 2024-04-10 | High | In Progress | 9 | T001
T003 | UI/UX Design Review | Sophie Lee | 2024-04-11 | 2024-04-15 | Medium | Pending | 5 | T002
T004 | Development Phase Start | Mike Brown | 2024-04-16 | 2024-05-31 | High | Not Started | 47 | T003
T005 | Testing & QA Cycle | Lisa Chen | 2024-06-01 | 2024-06-15 | High | Not Started | 15 | T004