## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Notes
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | High | Completed | Initial planning session with stakeholders.
T002 | Design Phase Review | Jane Smith | 2024-04-03 | 2024-04-10 | 7 | Medium | In Progress | Review wireframes and user flows.
T003 | Backend Development Start | Alex Johnson | 2024-04-11 | 2024-05-15 | 35 | High | Not Started | Begin API integration and database setup.
T004 | User Testing Session | Lisa Brown | 2024-05-20 | 2024-05-25 | 5 | High | Planned | Collect feedback from 10 beta users.
T005 | Final Deployment | Team Lead | 2024-06-01 | 2024-06-03 | 3 | Critical | Not Started | Go live on production servers.