## Worksheet
Task ID | Task Name | Assignee | Start Date | End Date | Duration (days) | Priority | Status | Notes
T001 | Project Planning Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | High | In Progress
T002 | Design Phase Kickoff | Jane Smith | 2024-04-03 | 2024-04-10 | 8 | Medium | Not Started
T003 | Prototype Development | Alex Johnson | 2024-04-11 | 2024-04-25 | 15 | High | Scheduled
T004 | User Testing Session | Sarah Lee | 2024-05-01 | 2024-05-03 | 3 | Medium | Planned
T005 | Final Review & Approval | Team Lead | 2024-05-15 | 2024-05-15 | 1 | High | Not Started