## Worksheet
Task ID | Task Name | Schedule Details |  |  | Responsible Person | Priority | Status
|  | Start Date | End Date | Duration
T001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 day | Alex Johnson | High | Planned
T002 | Market Research Phase | 2024-04-02 | 2024-04-15 | 14 days | Sarah Lee | Medium | Scheduled
T003 | Prototype Development | 2024-04-16 | 2024-05-10 | 35 days | Mark Thompson | High | In Progress
T004 | User Testing & Feedback | 2024-05-11 | 2024-05-25 | 15 days | Emily Chen | Medium | Pending Approval
T005 | Final Product Deployment | 2024-05-26 | 2024-05-31 | 6 days | David Ruiz | High | Planned