## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies | Progress (%) | Notes
T001 | Project Kickoff Meeting | Jane Doe | 2024-03-15 | 2024-03-15 | Completed | Low | None | 100% | All team members attended.
T002 | Requirements Finalization | John Smith | 2024-03-16 | 2024-03-25 | In Progress | Medium | T001 | 65% | Final review scheduled for 3/24.
T003 | UI/UX Design Phase | Lisa Chen | 2024-03-26 | 2024-04-10 | Pending | High | T002 | 20% | Client feedback due 4/5.
T004 | Development Sprint 1 | Mark Taylor | 2024-04-11 | 2024-04-25 | Not Started | High | T003 | 0% | Team will begin after design approval.
T005 | Testing & QA | Sarah Kim | 2024-05-01 | 2024-05-15 | Planned | Medium | T004 | 0% | Post-development phase.