## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Notes
T-001 | Project Kickoff Meeting | J. Smith | 2024-04-01 | 2024-04-01 | 1 | High | Pending | Confirm all team members and agenda.
T-002 | Requirements Gathering | A. Johnson | 2024-04-02 | 2024-04-10 | 9 | Medium | In Progress | Collect input from stakeholders.
T-003 | Design Phase Review | M. Lee | 2024-04-11 | 2024-04-15 | 5 | High | Scheduled | Review wireframes with product team.
T-004 | Development Phase Start | R. Davis | 2024-04-16 | 2024-05-31 | 47 | High | Not Started | Begin coding and integration.
T-005 | Testing & QA | S. White | 2024-06-01 | 2024-06-15 | 15 | Medium | Planned | Conduct unit and system testing.